## chatgpt
instance | seed | query | question | explanation | graph | n_reasons | n_connections | completeness | connectivity | imprecisions | complexity
1 | 1 | 2 | Why is activity 28 not completed at time period 76? | Activity 28 is not completed at time period 76 because it must be finished earlier to allow the timely start of activity 31, which in turn needs to be completed before activity 32 can begin. Delaying activity 28 would postpone the subsequent dependent activities and ultimately extend the overall project duration beyond the planned completion time of 43. | FALSE | 3 | 3 | 3 | 3 | 0
1 | 1 | 2 | Why is activity 28 not completed at time period 76? | Activity 28 is not completed at time period 76 because it plays a critical role in the sequence of dependent tasks that directly affect the project's completion time. It must be completed before activity 31 can begin, and activity 31, in turn, must finish before activity 32 can start. Since activity 32 marks the final point of the project at time period 43, any delay in completing activity 28 beyond its scheduled end at time 38 would postpone activity 31 and subsequently delay activity 32. This would extend the overall project completion time beyond the optimal finish at period 43, which the schedule is designed to avoid. | TRUE | 3 | 3 | 3 | 3 | 0
1 | 1 | 3 | Why is activity 24 not completed before time period 41? | Activity 24 is not completed before time period 41 because it cannot begin until its predecessors, including activity 23, are finished. Activity 23 depends on the completion of activity 22, which itself requires activities 16 and 17 to be completed first. The scheduling of these earlier activities, along with the need to coordinate limited resource availability, delays the start of activity 24, pushing its completion to time period 41. | FALSE | 8 | 13 | 4 | 4 | 0
1 | 1 | 3 | Why is activity 24 not completed before time period 41? | Activity 24 is not completed before time period 41 because it depends on a sequence of prior activities, each of which must finish before the next can begin. Specifically, activity 24 can only start once activity 23 is completed, which in turn must wait for activity 22. Activity 22 is delayed because both activities 16 and 17 must finish first, and they are subject to resource constraints, particularly with the limited availability of resource type 4 around time period 23. This scarcity affects the scheduling of activities using that resource, including 16 and 17, which pushes their completion times later. Consequently, the delays cascade through the dependency chain, ultimately preventing activity 24 from finishing any earlier than time period 41. | TRUE | 8 | 13 | 7 | 7 | 0
1 | 1 | 5 | Why is the subset of activities 30, 32 completed at time period 43? | The subset of activities 30 and 32 is completed at time period 43 because they are constrained by a sequence of dependent activities that must be completed beforehand. Activity 16 must finish before activity 22 can start, and activity 17 also depends on the completion of prior tasks. Activity 22 must be completed before activity 23, which then enables activity 24. Activity 24, in turn, must finish before activity 30 can begin. Finally, activity 32 cannot be completed until activity 30 ends. This chain of precedence constraints, along with the availability of resources at various time periods, determines the final schedule and leads to the completion of activities 30 and 32 at time period 43. | FALSE | 10 | 16 | 5 | 4 | 1
1 | 1 | 5 | Why is the subset of activities 30, 32 completed at time period 43? | The subset of activities 30 and 32 is completed at time period 43 due to a chain of interconnected dependencies and resource constraints that delay their execution. Activity 30 cannot begin until activity 24 is finished, which in turn depends on the completion of activity 23. Activity 23 is held up by activity 22, which itself requires the prior completion of activities 16 and 17. Activity 16 faces a delay because it shares limited resource availability with several other activities at a critical time, creating a bottleneck. Similarly, activity 17, which is also a prerequisite for activity 22, is impacted by the same resource contention. Since activity 30 is a direct predecessor of activity 32, any delay in its execution directly pushes the completion of activity 32 to the same time. These compounded dependencies and resource limitations prevent earlier completion and collectively determine that the subset finishes at time period 43. | TRUE | 10 | 16 | 7 | 8 | 0
1 | 1 | 7 | Why is the subset of activities 30, 32 completed at the same time period? | Activities 30 and 32 are completed at the same time because activity 32 depends on the completion of activity 30, which in turn relies on a sequence of preceding activities that must be completed in order. This chain of dependencies includes activities such as 16, 17, 22, 23, and 24, each of which must wait for its own predecessors to finish before starting. Additionally, resource limitations and scheduling constraints influence when these activities can start and finish, causing activity 30 to finish at a specific time that ultimately determines the completion time of activity 32. As a result, both activities align to conclude at the same time period. | FALSE | 10 | 16 | 2 | 2 | 2
1 | 1 | 7 | Why is the subset of activities 30, 32 completed at the same time period? | The subset of activities 30 and 32 is completed at the same time because of a chain of precedence constraints and resource limitations that dictate the earliest possible completion times. Activity 30 can only begin once activity 24 is finished, which in turn depends on activity 23. This backward chain continues through activities 22, 16, and 17, each of which must be completed in a specific sequence. Additionally, the completion of activity 30 is required before activity 32 can finish, thereby aligning their completion times. Compounding this is the limited availability of key resources—especially resource type 4 around time period 23—which delays certain predecessor activities. All these interconnected constraints push the latest activities toward the end of the schedule, ultimately causing activities 30 and 32 to complete simultaneously at time period 43, without extending the project further. | TRUE | 10 | 16 | 6 | 8 | 1
1 | 1 | 10 | Why is activity 29 completed at time period 26 instead of activity 17? | Activity 29 is completed at time period 26 instead of activity 17 because scheduling activity 17 earlier would delay the completion of the overall project. This is due to the need to first complete a sequence of dependent activities starting from activity 16, which must finish before activity 22 can begin. Activity 22 is a prerequisite for activity 23, which in turn is required for activity 24. Activity 24 must be completed before activity 30, which is essential for the final activity 32. Additionally, resource constraints—particularly the limited availability of resource type 4 around time period 21—further restrict when activity 17 can be scheduled without negatively impacting the overall project timeline. Therefore, prioritizing activity 29 at that time helps prevent extending the project beyond its minimum completion time. | FALSE | 8 | 9 | 7 | 4 | 0
1 | 1 | 10 | Why is activity 29 completed at time period 26 instead of activity 17? | Activity 29 is completed at time period 26 instead of activity 17 because of a chain of dependencies and resource limitations that impact the overall schedule. Specifically, resource type 4 is heavily demanded around time period 21, creating a bottleneck due to its simultaneous use by several other activities, including activities 10, 16, and 17. Activity 16, which is one of the key contributors to this bottleneck, must be completed before activity 22 can begin. In turn, activity 22 is a prerequisite for activity 23, which must finish before activity 24 can start. Activity 24 is needed for activity 30, which precedes the final activity, 32. Delaying any of these critical activities—such as prioritising activity 17 over activity 29—would extend the overall project duration beyond the optimal completion time of period 43. Therefore, the schedule prioritises activity 29's completion at time period 26 to prevent cascading delays that would push the project past its minimum completion time. | TRUE | 8 | 9 | 7 | 8 | 0
1 | 2 | 2 | Why is activity 28 not completed at time period 57? | Activity 28 is not completed at time period 57 because it must be finished in time to allow activity 30 to start, which in turn must be completed before the project-ending activity 32 can begin. Delaying activity 28 would postpone the start of activity 30, thereby extending the overall project duration beyond its minimum completion time of 47, violating the goal of minimising project completion time. | FALSE | 3 | 3 | 3 | 3 | 0
1 | 2 | 2 | Why is activity 28 not completed at time period 57? | Activity 28 is not completed at time period 57 because it must finish in time to allow activity 30 to start, which in turn must be completed before activity 32 can begin. Delaying activity 28 would postpone activity 30, which would push the entire project timeline beyond its current completion time of 47, extending the overall project duration unnecessarily. Therefore, activity 28 is scheduled to finish at time 39 to ensure that all subsequent activities can proceed without delay and the project is completed on time. | TRUE | 3 | 3 | 3 | 3 | 0
1 | 2 | 3 | Why is activity 28 not completed before time period 39? |  | FALSE | 17 | 70
1 | 2 | 3 | Why is activity 28 not completed before time period 39? |  | TRUE | 17 | 70
1 | 2 | 10 | Why is activity 19 completed at time period 24 instead of activity 14? |  | FALSE | 25 | 98
1 | 2 | 10 | Why is activity 19 completed at time period 24 instead of activity 14? |  | TRUE | 25 | 98
1 | 3 | 2 | Why is activity 15 not completed at time period 72? | Activity 15 is not completed at time period 72 because it must be finished earlier to allow dependent activities to start on time. Specifically, its timely completion enables activity 26 to begin, which in turn is necessary for the progression of activity 30 and ultimately activity 32. Delaying activity 15 would disrupt this sequence and extend the overall project duration beyond the scheduled completion time of 47. | FALSE | 4 | 4 | 4 | 4 | 0
1 | 3 | 2 | Why is activity 15 not completed at time period 72? | Activity 15 is not completed at time period 72 because it serves as an early prerequisite in a chain of dependent tasks that ultimately influence the project's completion time. Since activity 15 must be finished before activity 26 can start, and activity 26 is a prerequisite for activity 30, which in turn must be completed before activity 32—the final activity—any delay in activity 15 would cause a cascading delay through this entire chain. Such a delay would push the project’s completion beyond time period 47, which would violate the objective of minimising the project’s duration. Therefore, to prevent extending the project timeline, activity 15 is scheduled and completed earlier, ensuring the sequence of dependent tasks progresses without delay. | TRUE | 4 | 4 | 4 | 4 | 0
1 | 3 | 3 | Why is activity 32 not completed before time period 47? | Activity 32 is not completed before time period 47 because it depends on the completion of activities 29, 30, and 31. Activity 30 cannot start until activity 22 is completed, which in turn depends on the completion of activity 21. Since activity 21 requires both activities 8 and 18 to be finished, any delays in those activities will push the start of activity 21 and, consequently, the entire chain forward. Additionally, activity 31 depends on activity 28, which has its own prerequisites. This chain of dependencies, combined with resource limitations at certain times, causes the final activity to be scheduled at the latest point of the project, at time period 47. | FALSE | 14 | 28 | 7 | 7 | 1
1 | 3 | 3 | Why is activity 32 not completed before time period 47? | Activity 32 is not completed before time period 47 because it depends on the completion of activities 30 and 31, both of which experience delays due to a chain of precedence and resource constraints. Activity 30 cannot begin until activity 22 is completed, which itself is delayed by the need to finish activity 21. Activity 21 depends on the prior completion of both activities 8 and 18. These earlier activities are affected by resource availability—particularly, resource type 3 is in high demand during key periods, causing scheduling delays. Meanwhile, activity 31 is delayed by the need to complete activity 28, which also experiences constraints due to limited resource type 4 and dependency on preceding activities. These interlinked dependencies and resource bottlenecks ultimately prevent activity 32 from being completed any earlier than time period 47. | TRUE | 14 | 28 | 10 | 12 | 0
1 | 3 | 4 | Why is activity 25 not completed after time period 44? | Activity 25 is not completed after time period 44 because doing so would delay the start of activity 26, which in turn would postpone activity 30 and ultimately prevent activity 32 from being completed by time period 47. Since activity 25 is a predecessor in a critical chain of dependent tasks leading to the final project milestone, completing it any later would extend the overall project duration beyond the intended completion time. | FALSE | 4 | 4 | 4 | 3 | 0
1 | 3 | 4 | Why is activity 25 not completed after time period 44? | Activity 25 is not completed after time period 44 because it must finish in time to allow the subsequent activities—26, 30, and finally 32—to start and complete as scheduled. Any delay in completing activity 25 would postpone the start of activity 26, which in turn would delay activity 30, and ultimately prevent activity 32 from finishing on time. This sequence would extend the overall project duration beyond the planned completion at time 47, violating the goal of minimising the project completion time while respecting all precedence and resource constraints. | TRUE | 4 | 4 | 4 | 4 | 0
1 | 3 | 6 | Why is the subset of activities 17, 11, 14 not completed at time period 23? | The subset of activities 17, 11, and 14 is not completed at time period 23 because activity 17 depends on the completion of activity 11 before it can start. Since activity 11 finishes at time 21, activity 17 can only begin afterward and is completed at time 23. Therefore, the entire subset cannot be considered completed until activity 17 finishes at time 23. | FALSE | 2 | 3 | 1 | 1 | 1
1 | 3 | 6 | Why is the subset of activities 17, 11, 14 not completed at time period 23? | The subset of activities 17, 11, and 14 is not completed at time period 23 because activity 17 must be finished, and for it to start, activity 11 must be completed first. Since activity 11 is scheduled to finish at time period 21, activity 17 can only start after that, meaning it cannot be completed by time period 23. | TRUE | 2 | 3 | 2 | 3 | 0
1 | 3 | 8 | Why is the subset of activities 17, 11, 14 not completed at the same time period? | The subset of activities 17, 11, and 14 is not completed at the same time period because activity 17 depends on the completion of activity 11 before it can begin. This precedence relationship enforces a sequential order, preventing them from being executed simultaneously. | FALSE | 2 | 3 | 1 | 1 | 0
1 | 3 | 8 | Why is the subset of activities 17, 11, 14 not completed at the same time period? | The subset of activities 17, 11, and 14 is not completed at the same time because activity 17 depends on the completion of activity 11 before it can begin. Since activity 11 must finish first, it naturally delays the start of activity 17. This dependency creates a sequence rather than allowing the activities to run concurrently, which prevents them from being completed during the same time period. | TRUE | 2 | 3 | 1 | 1 | 0
1 | 3 | 10 | Why is activity 17 completed at time period 23 instead of activity 11? | Activity 17 is completed at time period 23 instead of activity 11 because it plays a critical role in the sequence of dependent tasks that directly affect the overall project duration. Specifically, activity 17 must be completed before activity 24 can start, which in turn is a prerequisite for activity 27, and subsequently for activity 28. Activity 28 is essential for the start of activity 31, which, along with activity 30, determines the earliest possible completion of the final activity, 32. Delaying activity 17 would delay this entire chain, potentially extending the total project duration beyond the current completion time. Therefore, prioritising the completion of activity 17 ensures that these dependencies are respected and the project remains on schedule. | FALSE | 12 | 21 | 7 | 7 | 0
1 | 3 | 10 | Why is activity 17 completed at time period 23 instead of activity 11? | Activity 17 is completed at time period 23 instead of activity 11 because it plays a critical role in a chain of dependent activities that directly influence the project's completion time. Specifically, activity 17 must be finished before activity 24 can begin. Activity 24, in turn, is a prerequisite for activity 27, which must be completed before activity 28 can start. Activity 28 then enables the start of activity 31, which is required for the final activity, 32. Delaying activity 17 would delay this entire sequence, ultimately extending the completion time of the project beyond the optimal point. Furthermore, activity 28 shares a resource that becomes scarce in later time periods, which adds pressure to complete preceding tasks like activity 17 earlier to avoid resource conflicts and delays. Therefore, prioritising the completion of activity 17 at time period 23 ensures the timely progression of critical dependent activities and helps minimise the overall project duration. | TRUE | 12 | 21 | 8 | 8 | 0
1 | 4 | 2 | Why is activity 23 not completed at time period 93? | Activity 23 is not completed at time period 93 because it plays a critical role in a chain of dependent tasks that ultimately determine the project’s overall completion time. Delaying activity 23 would delay the start of activity 25, which in turn would postpone activity 28 and all subsequent dependent activities. This would extend the duration of the project beyond its current completion time of 62, violating the objective of minimising the project completion time while adhering to precedence and resource constraints. | FALSE | 5 | 5 | 3 | 3 | 0
1 | 4 | 2 | Why is activity 23 not completed at time period 93? | Activity 23 is not completed at time period 93 because it plays a critical role in the sequence of activities that determine the overall project duration. It must be finished before activity 25 can begin. In turn, activity 25 is a prerequisite for activity 28, which must be completed before activity 30 can start. Since activity 30 is required for the final activity 32 to be completed, any delay in activity 23 would cascade through this chain, ultimately extending the project completion time beyond the current end point of time 62. Therefore, to avoid delaying the entire project, activity 23 must be completed much earlier than time 93. | TRUE | 5 | 5 | 5 | 5 | 0
1 | 4 | 10 | Why is activity 22 completed at time period 31 instead of activity 24? | Activity 22 is completed at time period 31 instead of activity 24 because the sequence of dependent activities leading to it—starting from activity 8 through activities 10, 12, and 20—takes precedence due to strict precedence constraints. Additionally, resource availability influences the schedule; for example, resource type 3 is heavily utilized around time period 24, which affects when certain activities can be scheduled. This combination of dependency chains and limited resource availability causes activity 24 to be delayed, allowing activity 22 to finish earlier within the constraints of the overall project schedule. | FALSE | 11 | 18 | 5 | 4 | 0
1 | 4 | 10 | Why is activity 22 completed at time period 31 instead of activity 24? | Activity 22 is completed at time period 31 instead of activity 24 because the availability of resource type 3 is limited at the time when both activities could potentially begin. This scarcity arises from other ongoing activities—such as 5, 8, and 27—that also require the same resource type. Activity 8, in particular, must be completed because it triggers a chain of dependent activities, including 10, 12, and ultimately 20 and 30, which are critical for the project to reach completion. These dependencies form a tightly connected sequence that affects the entire schedule, and any delay in one impacts the others. Allocating resources to activity 24 ahead of activity 22 would disrupt this chain, possibly delaying downstream activities like 29 and 30 and extending the project beyond its current completion time. Therefore, prioritizing activity 22 allows the project to maintain a schedule that avoids unnecessary delays and keeps the final completion within the target timeframe. | TRUE | 11 | 18 | 8 | 9 | 0
1 | 5 | 1 | Why is activity 25 completed at time period 28? |  | FALSE | 48 | 323
1 | 5 | 1 | Why is activity 25 completed at time period 28? |  | TRUE | 48 | 323
1 | 5 | 2 | Why is activity 17 not completed at time period 99? | Activity 17 is not completed at time period 99 because it must be finished early enough to allow a sequence of dependent activities—26, 28, 30, and ultimately 32—to start and complete on time. Delaying activity 17 would delay all subsequent dependent activities and extend the overall project duration beyond its current completion time of 39, violating the objective of minimising the project completion time. | FALSE | 5 | 5 | 5 | 5 | 0
1 | 5 | 2 | Why is activity 17 not completed at time period 99? | Activity 17 is not completed at time period 99 because it plays a critical role in a chain of dependent tasks that influence the overall project completion time. It must finish before activity 26 can begin, which in turn is a prerequisite for activity 28. Activity 28 must be completed before activity 30 starts, and activity 30 must finish before the final activity, 32, can occur. If activity 17 were delayed to time period 99, it would postpone the entire sequence of dependent activities and extend the project duration far beyond its completion time of 39, violating the goal of minimizing the overall project completion time. | TRUE | 5 | 5 | 5 | 5 | 0
1 | 5 | 4 | Why is activity 25 not completed after time period 28? |  | FALSE | 55 | 181
1 | 5 | 4 | Why is activity 25 not completed after time period 28? |  | TRUE | 55 | 181
1 | 5 | 6 | Why is the subset of activities 15, 11, 12 not completed at time period 22? |  | FALSE | 30 | 165
1 | 5 | 6 | Why is the subset of activities 15, 11, 12 not completed at time period 22? |  | TRUE | 30 | 165
1 | 5 | 9 | Why is activity 25 completed at time period 28 instead of time period 27? |  | FALSE | 40 | 192
1 | 5 | 9 | Why is activity 25 completed at time period 28 instead of time period 27? |  | TRUE | 40 | 192
1 | 6 | 2 | Why is activity 18 not completed at time period 102? | Activity 18 is not completed at time period 102 because it must be scheduled earlier to allow dependent activities—such as activities 20, 26, 29, and ultimately 32—to start and finish on time. Since activity 18 is a prerequisite for a chain of subsequent tasks that lead to the project's final activity, any delay in its completion would push back the entire sequence and extend the project beyond its current completion time of 48. Therefore, to meet the minimum project duration, activity 18 must be completed by time 38. | FALSE | 5 | 5 | 5 | 5 | 0
1 | 6 | 2 | Why is activity 18 not completed at time period 102? | Activity 18 is not completed at time period 102 because it serves as an essential step in a chain of dependent tasks that ultimately lead to the completion of the project. Specifically, activity 18 must be finished before activity 20 can begin, which in turn precedes activity 26. Activity 26 is a prerequisite for activity 29, and activity 29 must be completed before the final activity, 32, can occur. Delaying activity 18 would delay each subsequent task in this chain, ultimately extending the entire project timeline beyond the determined completion point at time period 48. Therefore, to ensure the project finishes on time, activity 18 must be completed by time 38, well before period 102. | TRUE | 5 | 5 | 5 | 5 | 0
1 | 6 | 5 | Why is the subset of activities 26, 31 completed at time period 47? |  | FALSE | 32 | 151
1 | 6 | 5 | Why is the subset of activities 26, 31 completed at time period 47? |  | TRUE | 32 | 151
1 | 6 | 6 | Why is the subset of activities 19, 16 not completed at time period 24? | The subset of activities 19 and 16 is not completed at time period 24 because activity 19 depends on the completion of activity 16. Since activity 16 finishes at time 23 and activity 19 starts and finishes at time 24, both activities cannot be considered completed until activity 19 is done. Therefore, the entire subset is only completed at the end of time period 24. | FALSE | 2 | 3 | 1 | 1 | 1
1 | 6 | 6 | Why is the subset of activities 19, 16 not completed at time period 24? | The subset of activities 19 and 16 is not completed at time period 24 because activity 19 must still be completed at that time, and it can only start after activity 16 finishes. Since activity 16 finishes at time 23, activity 19 begins at time 24, making it impossible for both activities to be completed by that same time period. | TRUE | 2 | 3 | 2 | 3 | 0
1 | 6 | 7 | Why is the subset of activities 26, 31 completed at the same time period? |  | FALSE | 32 | 153
1 | 6 | 7 | Why is the subset of activities 26, 31 completed at the same time period? |  | TRUE | 32 | 153
1 | 6 | 8 | Why is the subset of activities 19, 16 not completed at the same time period? |  | FALSE | 19 | 98
1 | 6 | 8 | Why is the subset of activities 19, 16 not completed at the same time period? |  | TRUE | 19 | 98
1 | 6 | 10 | Why is activity 19 completed at time period 24 instead of activity 9? |  | FALSE | 21 | 59
1 | 6 | 10 | Why is activity 19 completed at time period 24 instead of activity 9? |  | TRUE | 21 | 59
1 | 7 | 2 | Why is activity 15 not completed at time period 60? | Activity 15 is not completed at time period 60 because it must be finished in order for activity 19 to begin. Activity 19, in turn, is a necessary predecessor for activity 29, which must be completed before the final activity, 32, can occur. Delaying activity 15 would delay all subsequent dependent activities and ultimately extend the overall project duration beyond the desired completion time. Therefore, activity 15 must be scheduled earlier to allow the rest of the project to finish by time period 60. | FALSE | 4 | 4 | 4 | 4 | 0
1 | 7 | 2 | Why is activity 15 not completed at time period 60? | Activity 15 is not completed at time period 60 because it must be finished before activity 19 can begin. Since activity 19 is a prerequisite for activity 29, and activity 29 must be completed before activity 32 starts, any delay in activity 15 would delay the entire chain of dependent activities. If activity 15 were still ongoing at time period 60, it would prevent the timely start and completion of subsequent tasks, ultimately extending the project beyond its intended completion time. Therefore, to ensure the project finishes on schedule, activity 15 must be completed earlier. | TRUE | 4 | 4 | 4 | 4 | 0
1 | 7 | 4 | Why is activity 25 not completed after time period 49? | Activity 25 is not completed after time period 49 because delaying its completion would postpone the start of activity 28, which in turn would delay activity 31. Since activity 31 must be completed before activity 32 can begin, any delay in activity 25 would ultimately extend the overall project completion time beyond the targeted time period of 60. To ensure the schedule meets the project deadline, activity 25 must be completed by time 49. | FALSE | 4 | 4 | 4 | 4 | 0
1 | 7 | 4 | Why is activity 25 not completed after time period 49? | Activity 25 is not completed after time period 49 because it must finish in time to allow activity 28 to begin, which in turn is a prerequisite for activity 31. Since activity 31 must be completed before the project can end with activity 32, any delay in completing activity 25 would cause a chain reaction, ultimately extending the overall project duration beyond the planned completion time of 60. To avoid this and minimize the project completion time, activity 25 is scheduled to finish by time 49. | TRUE | 4 | 4 | 4 | 4 | 0
1 | 8 | 1 | Why is activity 25 completed at time period 35? |  | FALSE | 22 | 95
1 | 8 | 1 | Why is activity 25 completed at time period 35? |  | TRUE | 22 | 95
1 | 8 | 2 | Why is activity 29 not completed at time period 118? | Activity 29 is not completed at time period 118 because it must be finished before activity 32 can begin, and activity 32 is scheduled to start and finish at time period 53. Delaying activity 29 until time period 118 would postpone the start of activity 32, extending the overall project duration beyond the planned completion time of 53. Therefore, to meet the project deadline, activity 29 is scheduled to finish by time period 53. | FALSE | 2 | 2 | 2 | 2 | 0
1 | 8 | 2 | Why is activity 29 not completed at time period 118? | Activity 29 is not completed at time period 118 because it must finish before activity 32 can begin. Since activity 32 marks the project’s end and occurs at time 53, delaying activity 29 would extend the overall project duration beyond that point, violating the requirement to minimise the project completion time. | TRUE | 2 | 2 | 2 | 2 | 0
1 | 8 | 3 | Why is activity 23 not completed before time period 26? | Activity 23 is not completed before time period 26 because it cannot begin until activity 9 is finished. Since activity 9 ends at time 25, activity 23 can only start at time 26. This scheduling respects the precedence constraint that requires activity 9 to be completed before activity 23 can begin. | FALSE | 13 | 29 | 1 | 1 | 0
1 | 8 | 3 | Why is activity 23 not completed before time period 26? | Activity 23 is not completed before time period 26 because it depends on the completion of activity 9, which finishes at time 25. Activity 9 itself is delayed due to both precedence constraints and limited availability of resource type 2 during earlier time periods. Resource conflicts involving multiple activities, including 14 and 9, create bottlenecks that prevent earlier scheduling. These delays propagate through the project schedule, as activity 14 must be completed before activity 16 can begin, which in turn delays activity 18 and the dependent chain of activities leading up to the project’s completion. As a result of these precedence and resource constraints, activity 23 can only be scheduled at time 26. | TRUE | 13 | 29 | 9 | 9 | 0
1 | 8 | 4 | Why is activity 25 not completed after time period 35? | Activity 25 is not completed after time period 35 because it must finish in time to allow activity 26 to start, which in turn is a prerequisite for activity 28. Activity 28 must be completed before activity 31 can begin, and both activities 29 and 31 must finish before activity 32—the final activity—can occur. Delaying activity 25 would delay the entire chain of dependent activities, ultimately extending the project beyond its minimum completion time of 53. Therefore, activity 25 must be completed by time 35 to ensure that all subsequent tasks can proceed on schedule and the overall project duration is minimized. | FALSE | 11 | 38 | 6 | 5 | 0
1 | 8 | 4 | Why is activity 25 not completed after time period 35? | Activity 25 is not completed after time period 35 because it must finish in time to allow activity 26 to start, which is a necessary predecessor for activity 28. This chain continues as activity 28 must be completed before activity 31 can begin, and both activities 29 and 31 must finish before activity 32, the final activity, can be completed. Delaying activity 25 would postpone this entire sequence, ultimately extending the project beyond its minimum completion time of 53. Additionally, resource limitations—particularly the heavy demand on resource type 2 in later time periods—would further constrain the schedule if activity 25 were delayed, as it would then compete with other resource-intensive activities. Therefore, completing activity 25 by time 35 is essential to maintaining the critical path and achieving the shortest possible project duration. | TRUE | 11 | 38 | 8 | 7 | 0
1 | 8 | 9 | Why is activity 25 completed at time period 35 instead of time period 34? | Activity 25 is completed at time period 35 instead of 34 because it requires a significant amount of resource type 2, which is also heavily demanded by several other activities during overlapping time periods. Due to the limited availability of this resource, activity 25 could not start earlier, even though its only predecessor, activity 2, was already completed. The scheduling had to be adjusted to respect both precedence and resource constraints, leading to a later completion time. | FALSE | 13 | 30 | 2 | 2 | 1
1 | 8 | 9 | Why is activity 25 completed at time period 35 instead of time period 34? | Activity 25 is completed at time period 35 instead of 34 due to limited availability of resource type 2 at crucial earlier time periods, particularly around time 25. This scarcity arises because several other activities—such as 9 and 14—also demand the same resource simultaneously. These activities cannot be delayed as they are critical to the progression of dependent tasks, such as activities 16 and 18, which in turn affect the scheduling of later activities like 21 and 29, ultimately determining the overall project duration. Delaying activity 25 by one time unit ensures the required resources are available without disrupting the sequence of dependent tasks, thereby avoiding any extension of the total project completion time beyond the optimal. | TRUE | 13 | 30 | 9 | 10 | 0
1 | 8 | 10 | Why is activity 7 completed at time period 34 instead of activity 25? | Activity 7 is completed at time period 34 instead of activity 25 because other activities with higher priority due to precedence relationships and resource demands were scheduled earlier. Specifically, activities such as 9, 14, and 16 needed to be completed first to allow the progression of critical path tasks like activity 18 and beyond. Additionally, limited availability of a key resource during overlapping time periods delayed the scheduling of some activities, including activity 25. To avoid delaying the overall project completion time, preference was given to critical activities that directly impact the project's finish, while non-critical activities like 7 were scheduled within available resource windows without extending the project duration. | FALSE | 13 | 30 | 7 | 2 | 1
1 | 8 | 10 | Why is activity 7 completed at time period 34 instead of activity 25? | Activity 7 is completed at time period 34 instead of activity 25 due to resource constraints, particularly involving resource type 2. At several key time periods—such as 11, 15, 20, and 25—this resource is heavily demanded by multiple other activities, including 14, 23, 25, 27, 3, 4, 5, and 9. Activities 14 and 9 are critical, as they must be completed before subsequent dependent activities like 16 and 18 can begin. These, in turn, influence the timing of downstream tasks such as activities 21 and 29, which ultimately affect the completion of the entire project. Delaying any of these crucial activities due to resource conflicts would postpone the final milestone. Therefore, activity 25 is scheduled later to prioritize the execution of activities on the critical path, allowing activity 7 to be completed earlier within the resource constraints. | TRUE | 13 | 30 | 11 | 17 | 0
1 | 9 | 2 | Why is activity 28 not completed at time period 113? | Activity 28 is not completed at time period 113 because it must finish in time to allow activity 30 to start, which in turn must be completed before activity 32 can begin. Delaying activity 28 to time period 113 would prevent these dependent activities from starting on schedule and would extend the overall project duration beyond time period 49, violating the objective of minimising the project completion time. | FALSE | 3 | 3 | 3 | 3 | 0
1 | 9 | 2 | Why is activity 28 not completed at time period 113? | Activity 28 is not completed at time period 113 because it must finish early enough to allow activity 30 to begin on time. Since activity 30 is a direct prerequisite for activity 32, any delay in activity 28 would delay the entire chain of dependent activities. This would ultimately extend the project's total duration beyond time period 49, which contradicts the goal of minimizing the project completion time. Therefore, to avoid project delays, activity 28 is scheduled to be completed by time period 45. | TRUE | 3 | 3 | 3 | 3 | 0
1 | 9 | 5 | Why is the subset of activities 30, 32 completed at time period 49? |  | FALSE | 42 | 240
1 | 9 | 5 | Why is the subset of activities 30, 32 completed at time period 49? |  | TRUE | 42 | 240
1 | 9 | 6 | Why is the subset of activities 13, 15 not completed at time period 25? |  | FALSE | 22 | 75
1 | 9 | 6 | Why is the subset of activities 13, 15 not completed at time period 25? |  | TRUE | 22 | 75
1 | 9 | 7 | Why is the subset of activities 30, 32 completed at the same time period? |  | FALSE | 42 | 240
1 | 9 | 7 | Why is the subset of activities 30, 32 completed at the same time period? |  | TRUE | 42 | 240
1 | 9 | 8 | Why is the subset of activities 13, 15 not completed at the same time period? |  | FALSE | 45 | 250
1 | 9 | 8 | Why is the subset of activities 13, 15 not completed at the same time period? |  | TRUE | 45 | 250
1 | 9 | 10 | Why is activity 13 completed at time period 25 instead of activity 24? |  | FALSE | 42 | 250
1 | 9 | 10 | Why is activity 13 completed at time period 25 instead of activity 24? |  | TRUE | 42 | 250
1 | 10 | 2 | Why is activity 30 not completed at time period 98? | Activity 30 is not completed at time period 98 because it must be finished before activity 32 can start, and activity 32 is scheduled to begin and end at time period 45. Delaying activity 30 until time period 98 would extend the project completion time beyond 45, violating the goal of minimizing the overall project duration. | FALSE | 2 | 2 | 2 | 2 | 0
1 | 10 | 2 | Why is activity 30 not completed at time period 98? | Activity 30 is not completed at time period 98 because it must be finished before activity 32 can begin. Since activity 32 marks the end of the project and occurs at time 45, delaying activity 30 until time 98 would push the project's completion well beyond its actual endpoint. This would violate the precedence constraints and unnecessarily extend the project duration. | TRUE | 2 | 2 | 2 | 2 | 0
1 | 10 | 3 | Why is activity 31 not completed before time period 45? |  | FALSE | 34 | 200
1 | 10 | 3 | Why is activity 31 not completed before time period 45? |  | TRUE | 34 | 200
1 | 10 | 4 | Why is activity 25 not completed after time period 34? | Activity 25 is not completed after time period 34 because it must be finished in time to allow the timely start of activity 27, which depends on it. Delaying activity 25 would postpone activity 27, which in turn would delay activity 31 and ultimately activity 32. Since activity 32 marks the end of the project, any delay in this chain would extend the overall project duration beyond the current completion time of 45, which the schedule aims to avoid. | FALSE | 4 | 4 | 4 | 4 | 0
1 | 10 | 4 | Why is activity 25 not completed after time period 34? | Activity 25 is not completed after time period 34 because it must be finished in time for activity 27 to begin, as activity 27 cannot start until activity 25 is complete. Delaying activity 25 would delay the start of activity 27, which in turn would postpone activity 31. Since activity 31 must be finished before activity 32 can begin, any delay in activity 25 would ultimately push the completion of activity 32 beyond time period 45, extending the overall project duration. Therefore, to prevent extending the project timeline, activity 25 must be completed by time period 34. | TRUE | 4 | 4 | 4 | 4 | 0
1 | 10 | 10 | Why is activity 16 completed at time period 23 instead of activity 12? |  | FALSE | 30 | 200
1 | 10 | 10 | Why is activity 16 completed at time period 23 instead of activity 12? |  | TRUE | 30 | 200
2 | 1 | 2 | Why is activity 29 not completed at time period 91? | Activity 29 is not completed at time period 91 because it must be finished before activity 32 can begin, and activity 32 is scheduled to start and finish at time period 38. Delaying activity 29 until time 91 would extend the overall project duration beyond time 38, violating the goal of minimising the project completion time while respecting precedence constraints. | FALSE | 2 | 2 | 2 | 2 | 0
2 | 1 | 2 | Why is activity 29 not completed at time period 91? | Activity 29 is not completed at time period 91 because it must be finished before activity 32 can begin. Since activity 32 marks the end of the project and is scheduled to start and complete at time period 38, delaying activity 29 until time period 91 would push the project's completion well beyond the planned end time. This would violate the objective of minimising the overall project duration, which is achieved by completing all necessary predecessor activities, including activity 29, by time period 38. | TRUE | 2 | 2 | 2 | 2 | 0
2 | 1 | 3 | Why is activity 29 not completed before time period 37? |  | FALSE | 19 | 40
2 | 1 | 3 | Why is activity 29 not completed before time period 37? |  | TRUE | 19 | 40
2 | 1 | 9 | Why is activity 25 completed at time period 32 instead of time period 31? |  | FALSE | 20 | 38
2 | 1 | 9 | Why is activity 25 completed at time period 32 instead of time period 31? |  | TRUE | 20 | 38
2 | 1 | 10 | Why is activity 14 completed at time period 17 instead of activity 15? |  | FALSE | 19 | 45
2 | 1 | 10 | Why is activity 14 completed at time period 17 instead of activity 15? |  | TRUE | 19 | 45
2 | 2 | 2 | Why is activity 22 not completed at time period 116? | Activity 22 is not completed at time period 116 because it is scheduled much earlier in the project to ensure that dependent activities, such as activity 31 and ultimately activity 32, can start and finish on time. Delaying the completion of activity 22 to time period 116 would postpone the start of activity 31, which in turn would delay activity 32. Since activity 32 marks the end of the project, this delay would extend the overall project duration beyond time period 51, violating the objective of minimising the project completion time. | FALSE | 3 | 3 | 3 | 3 | 0
2 | 2 | 2 | Why is activity 22 not completed at time period 116? | Activity 22 is not completed at time period 116 because it plays a critical role in the sequence of activities that determine the overall project completion time. It must be finished before activity 31 can begin, and activity 31, in turn, must be completed before activity 32 can start. Since activity 32 marks the end of the project and is scheduled to finish at time period 51, delaying activity 22 beyond this point would extend the project duration. Therefore, to ensure the project finishes on time, activity 22 must be completed well before time period 116. | TRUE | 3 | 3 | 3 | 3 | 0
2 | 2 | 4 | Why is activity 25 not completed after time period 32? | Activity 25 is completed by time period 32 because it must finish before activity 28 can begin. Since activity 28 is a prerequisite for activity 30, which in turn must finish before the final activity 32, delaying activity 25 would delay the entire sequence and extend the overall project duration beyond the target of time period 51. To ensure the project completes on time, activity 25 must be scheduled to finish no later than time period 32. | FALSE | 4 | 4 | 4 | 4 | 0
2 | 2 | 4 | Why is activity 25 not completed after time period 32? | Activity 25 is not completed after time period 32 because it must be finished before activity 28 can begin. Activity 28, in turn, is a necessary predecessor of activity 30, which must be completed before activity 32 can start. Since activity 32 marks the end of the project, any delay in completing activity 25 would delay the subsequent dependent activities, ultimately extending the overall project duration beyond the planned completion time of 51. Therefore, completing activity 25 by time 32 is essential to ensure the project finishes on schedule. | TRUE | 4 | 4 | 4 | 4 | 0
2 | 2 | 10 | Why is activity 26 completed at time period 21 instead of activity 18? | Activity 26 is completed at time period 21 instead of activity 18 because it depends on the completion of activity 12, which in turn cannot start until activity 5 is finished. Activity 5 must first finish before activity 12 can begin, delaying the start of activity 26. Additionally, resource availability constraints influence when activities can be scheduled. At certain time periods, resource 1 is heavily utilized by other activities, which can delay the start of activity 18 despite it being an earlier predecessor. As a result, activity 26, which requires fewer resource units and has a shorter duration, is able to complete earlier in the schedule. | FALSE | 11 | 24 | 5 | 7 | 1
2 | 2 | 10 | Why is activity 26 completed at time period 21 instead of activity 18? | Activity 26 is completed at time period 21 instead of activity 18 because it depends on the completion of activity 12, which itself cannot start until activity 5 is finished. Activity 5 is delayed due to earlier resource constraints, especiaçlly the limited availability of resource type 1, which is heavily used by other concurrent activities. Additionally, activity 26 must finish before activity 29 can begin, which is on the critical path leading to the final activity, and any delay in this sequence would extend the overall project duration. Therefore, prioritising activity 26 over activity 18 helps maintain the shortest possible completion time for the entire project, ensuring that downstream dependencies are not delayed. | TRUE | 11 | 24 | 6 | 6 | 1
2 | 3 | 1 | Why is activity 25 completed at time period 40? | Activity 25 is completed at time period 40 because it cannot start until all its predecessor activities—11, 17, and 20—are finished. Among these, activity 17 finishes at time 36, which delays the start of activity 25 until time 37. Additionally, resource constraints and scheduling of concurrent activities may influence the exact timing, but the primary reason is the dependency on the completion of its predecessors. | FALSE | 10 | 19 | 1 | 1 | 0
2 | 3 | 1 | Why is activity 25 completed at time period 40? | Activity 25 is completed at time period 40 because it cannot begin until activity 17 is finished, which itself is delayed due to resource constraints affecting its scheduling. Activity 17 relies on limited availability of resource type 2, which is heavily used by several other activities around the same time. These resource conflicts delay the completion of activity 17, which in turn postpones the start of activity 25. Since activity 25 also depends on the completion of activities 11 and 20, any delays in those, combined with resource contention, push activity 25’s completion to time period 40. This timing is critical because activity 25 must finish before activity 29 can start, and the overall project schedule depends on maintaining this sequence to avoid extending the project beyond its final completion time. | TRUE | 10 | 19 | 7 | 7 | 0
2 | 3 | 2 | Why is activity 23 not completed at time period 150? | Activity 23 is not completed at time period 150 because doing so would delay the start of activity 28, which in turn would postpone activity 30 and ultimately delay the completion of activity 32. Since activity 32 marks the end of the project, any delay in this chain would extend the overall project duration beyond the optimal completion time of 43. To minimise the project completion time, activity 23 must be scheduled earlier, respecting its precedence and resource constraints. | FALSE | 4 | 4 | 4 | 4 | 0
2 | 3 | 2 | Why is activity 23 not completed at time period 150? | Activity 23 is not completed at time period 150 because it plays a crucial role in a chain of dependent activities that ultimately determine the project’s overall completion time. Since activity 23 must be completed before activity 28 can begin, and activity 28 must finish before activity 30 starts, any delay in activity 23 would delay the subsequent activities. Activity 30, in turn, is a direct predecessor of activity 32, which marks the end of the project. Therefore, completing activity 23 much later, such as at time period 150, would delay the entire sequence and extend the project duration significantly beyond its actual completion at time period 43. To ensure the project finishes on time, activity 23 must be completed earlier, respecting its position within the tightly linked schedule. | TRUE | 4 | 4 | 4 | 4 | 0
2 | 3 | 3 | Why is activity 26 not completed before time period 35? |  | FALSE | 18 | 34
2 | 3 | 3 | Why is activity 26 not completed before time period 35? |  | TRUE | 18 | 34
2 | 3 | 4 | Why is activity 25 not completed after time period 40? | Activity 25 is not completed after time period 40 because it must finish in time for activity 29 to start, as activity 25 is a direct predecessor of activity 29. Delaying activity 25 would delay activity 29, which in turn would delay activity 32, the final activity. This would extend the overall project duration beyond the current completion time of 43, which would violate the objective of minimising the project completion time. | FALSE | 3 | 3 | 3 | 3 | 0
2 | 3 | 4 | Why is activity 25 not completed after time period 40? | Activity 25 is not completed after time period 40 because it must finish before activity 29 can begin. Since activity 29 is a necessary predecessor for activity 32, any delay in completing activity 25 would delay activity 29 and subsequently postpone the start of activity 32. This would extend the overall project duration beyond the current completion time of 43, violating the goal of minimising the project completion time. Therefore, activity 25 is scheduled to finish by time period 40 to ensure the project stays on schedule. | TRUE | 3 | 3 | 3 | 3 | 0
2 | 3 | 5 | Why is the subset of activities 29, 30, 32 completed at time period 43? | The subset of activities 29, 30, and 32 is completed at time period 43 due to a combination of precedence constraints and resource availability. Activities 29 and 30 depend on the completion of earlier activities, including 17, 25, and 28. These dependencies delay their start times until the required predecessors are finished. Additionally, resource constraints, particularly the limited availability of resource type 2 during certain time periods, prevent some activities from starting earlier even if their predecessors are complete. Activity 32, which has no duration, can only be completed once both 29 and 30 are finished, setting the overall completion time of this subset at time period 43. | FALSE | 10 | 22 | 6 | 6 | 1
2 | 3 | 5 | Why is the subset of activities 29, 30, 32 completed at time period 43? | The subset of activities 29, 30, and 32 is completed at time period 43 due to a combination of precedence and resource constraints that propagate through the project schedule. Activity 29 cannot begin until activity 25 is completed, which itself depends on the completion of activity 17. Similarly, activity 30 must wait for activity 28 to finish, and activity 28 is constrained by resource availability, particularly the scarcity of resource type 2 around its scheduled period. This scarcity is intensified by the concurrent demand from multiple other activities, which limits the possibility of scheduling resource-heavy tasks earlier. Additionally, both activities 29 and 30 must be completed before activity 32 can finish, and delaying either would push the project beyond time period 43. Therefore, the dependencies and resource limitations collectively determine that activities 29 and 30 finish at time 43, allowing activity 32 to be completed at the same time, thus marking the end of the project. | TRUE | 10 | 22 | 8 | 8 | 0
2 | 3 | 6 | Why is the subset of activities 24, 16, 19 not completed at time period 25? | The subset of activities 24, 16, and 19 is not completed at time period 25 because each of these activities has specific durations and dependencies that extend their execution beyond this point in time. Activity 19, for example, runs until time 24 and is a necessary predecessor for activity 21, which itself is part of a chain of dependent activities leading up to the final activity of the project. Delays or overlaps in these activities influence the start and end times of subsequent tasks, and completing them earlier would disrupt the sequence required to satisfy both precedence and resource constraints. As a result, their completion timeline contributes to the overall project duration, which extends to time period 43. | FALSE | 5 | 5 | 2 | 2 | 1
2 | 3 | 6 | Why is the subset of activities 24, 16, 19 not completed at time period 25? | The subset of activities 24, 16, and 19 is not completed by time period 25 because activity 19 plays a critical role in a chain of dependent tasks that ultimately impact the overall project duration. Since activity 19 must finish before activity 21 can start, and activity 21 is a prerequisite for activity 22, which in turn must be completed before activity 30 can begin, any delay in activity 19 propagates through this sequence. Activity 30 is one of the final tasks required before the project can be completed with activity 32. Therefore, the timing of activity 19 affects not just its own completion but also contributes to extending the project timeline beyond period 43. This interconnected dependency delays the completion of the entire subset by time period 25. | TRUE | 5 | 5 | 4 | 4 | 0
2 | 3 | 7 | Why is the subset of activities 29, 30, 32 completed at the same time period? | The subset of activities 29, 30, and 32 is completed at the same time period because their scheduling is tightly constrained by both precedence and resource availability. Activities 29 and 30 depend on the completion of earlier tasks including activities 25 and 28, which themselves cannot start until other dependencies like activity 17 are finished. Additionally, constraints on resource availability delay the start of some activities, such as activity 28, which must wait for sufficient units of resource type 2. These delays cascade through the schedule, causing activities 29 and 30 to complete simultaneously. Since activity 32 depends on the completion of both 29 and 30, it is also scheduled to finish at the same time, marking the end of the project without extending its duration unnecessarily. | FALSE | 10 | 22 | 7 | 7 | 1
2 | 3 | 7 | Why is the subset of activities 29, 30, 32 completed at the same time period? | The subset of activities 29, 30, and 32 is completed at the same time period because of how their dependencies and resource constraints align. Activity 29 cannot begin until activity 25 is completed, which itself depends on the completion of activity 17. Similarly, activity 30 must wait for activity 28 to finish, which is delayed due to limited availability of resource type 2. Both activities 29 and 30 are prerequisites for activity 32, meaning that 32 cannot be completed until both are done. The overlapping dependencies and the delays caused by resource scarcity lead to activities 29 and 30 finishing at the same time. As a result, activity 32, which has no duration, is also completed at that same time, since it must wait for both 29 and 30. Any delay in these chains would extend the project beyond the final time period, so their synchronization ensures the project finishes on time. | TRUE | 10 | 22 | 7 | 7 | 0
2 | 3 | 8 | Why is the subset of activities 24, 16, 19 not completed at the same time period? | The subset of activities 24, 16, and 19 is not completed at the same time period due to both precedence constraints and limited resource availability. Activity 19 cannot start until activity 6 is completed, which delays its initiation. Similarly, activity 24 depends on the completion of activities 6 and 18, and activity 16 is constrained by the completion of activity 14. Additionally, these activities compete for limited resources, especially resource type 2, which is heavily used during overlapping time periods. This scarcity prevents them from being scheduled simultaneously, forcing their execution to be staggered over different time intervals. | FALSE | 14 | 30 | 3 | 3 | 2
2 | 3 | 8 | Why is the subset of activities 24, 16, 19 not completed at the same time period? | The subset of activities 24, 16, and 19 is not completed at the same time period due to a combination of precedence constraints and resource limitations. Activity 19 cannot start until activity 6 is completed, which itself depends on earlier activities and competes for limited resource availability. At critical time periods, particularly around time 19, resource type 2 is heavily demanded by multiple ongoing activities, including 12, 19, and 24, which delays their execution. Additionally, activity 16 depends on the completion of activity 14, introducing further scheduling constraints. These interconnected dependencies and resource contentions cause the activities in question to be scheduled at different times rather than being completed simultaneously. | TRUE | 14 | 30 | 3 | 7 | 1
2 | 3 | 9 | Why is activity 25 completed at time period 40 instead of time period 39? | Activity 25 is completed at time period 40 instead of 39 because it cannot start until activity 17 is finished, which completes at time period 36. Given that activity 25 has a duration of 4 time units, the earliest it can be completed is time period 40. This scheduling respects the precedence constraint that requires activity 17 to be completed before activity 25 begins. | FALSE | 9 | 16 | 1 | 1 | 0
2 | 3 | 9 | Why is activity 25 completed at time period 40 instead of time period 39? | Activity 25 is completed at time period 40 instead of 39 because it cannot begin until all its predecessor activities, including activity 17, are completed. Activity 17 itself experiences a delay due to limited availability of resource type 2, which is heavily used by several other activities around the same time. This scarcity affects when activity 17 can be scheduled, and since activity 25 depends on it, the delay propagates. Additionally, other dependent activities like activity 28 and activity 30 are also influenced by the same resource constraints, contributing further to the timing of subsequent tasks. These interconnected dependencies and resource limitations result in activity 25 being pushed to complete at time period 40. | TRUE | 9 | 16 | 4 | 4 | 0
2 | 5 | 2 | Why is activity 24 not completed at time period 167? | Activity 24 is not completed at time period 167 because it must be finished in time to allow the subsequent activities, specifically activity 31 and then activity 32, to start and finish by the project's end at time period 51. Delaying activity 24 beyond this point would prevent activity 31 from starting on time, which in turn would delay activity 32, extending the overall project duration beyond the planned completion time. Therefore, activity 24 is scheduled to finish at time 50 to ensure that all dependent activities can be completed by time 51, maintaining the minimum project completion time. | FALSE | 3 | 3 | 3 | 3 | 0
2 | 5 | 2 | Why is activity 24 not completed at time period 167? | Activity 24 is not completed at time period 167 because it plays a critical role in the timely progression of the final stages of the project. It must be completed before activity 31 can begin, and activity 31, in turn, is a necessary predecessor for activity 32, which marks the end of the project. Delaying activity 24 would delay activity 31, which would consequently postpone the completion of activity 32. This chain of dependencies means that any delay in activity 24 would extend the overall project duration beyond time period 51, which contradicts the goal of minimizing the project completion time. Therefore, activity 24 is scheduled earlier to ensure the project finishes as early as possible. | TRUE | 3 | 3 | 3 | 3 | 0
2 | 5 | 4 | Why is activity 25 not completed after time period 42? | Activity 25 is not completed after time period 42 because it must finish in time to allow activity 30 to start at time 43. Activity 30 depends on the completion of activity 25, and any delay in activity 25 would postpone activity 30. Since activity 30 must finish before activity 32 can start, delaying it would extend the overall project completion time beyond the planned end at time 51. Therefore, activity 25 is scheduled to finish by time 42 to ensure that all dependent activities can proceed without delaying the project. | FALSE | 3 | 3 | 3 | 3 | 0
2 | 5 | 4 | Why is activity 25 not completed after time period 42? | Activity 25 is not completed after time period 42 because it must finish in time to allow activity 30 to start, as activity 30 depends on the completion of activity 25. In turn, activity 30 must finish before activity 32 can begin. Delaying activity 25 would push back the start of activity 30, which would then delay activity 32 and extend the overall project duration beyond time period 51. Therefore, to prevent extending the project's completion time, activity 25 must be completed by time period 42. | TRUE | 3 | 3 | 3 | 3 | 0
2 | 5 | 5 | Why is the subset of activities 30, 31, 32 completed at time period 51? | The subset of activities 30, 31, and 32 is completed at time period 51 due to a combination of precedence constraints and resource limitations throughout the project. Activities 30 and 31 depend on the completion of several earlier tasks, such as activities 24, 26, and 27, which themselves are delayed due to the need to wait for their own predecessors and the limited availability of shared resources. For example, activity 30 must wait for activity 27, and activity 31 requires both activities 24 and 28 to finish. Since activity 28 depends on the completion of activity 26, which in turn requires activity 21, delays propagate through the schedule. Furthermore, resource constraints, particularly for shared resource types, cause additional scheduling conflicts that prevent tasks from being executed in parallel when desired. As a result, activities 30 and 31 cannot start earlier, pushing their completion to time period 51. Activity 32, having both 30 and 31 as predecessors, also completes at this point, marking the end of the project. | FALSE | 15 | 42 | 7 | 7 | 1
2 | 5 | 5 | Why is the subset of activities 30, 31, 32 completed at time period 51? | The subset of activities 30, 31, and 32 is completed at time period 51 due to a chain of precedence and resource constraints that delay their execution. Activity 30 cannot begin until activity 27 is finished, and activity 27 itself is delayed because of limited availability of resource type 4, which is shared with other resource-intensive activities like 21 and 24 around the same time period. Similarly, activity 31 depends on the completion of activities 24 and 28. Activity 24 is delayed due to both its predecessors and competition for scarce resources, while activity 28 cannot start until activity 26 is completed, which in turn depends on activity 21 finishing first. These interdependencies and the competition for limited resources, especially resource type 4, cause delays that push the completion of activities 30 and 31 to time period 51. Since activity 32 depends on both 30 and 31, it also finishes at time 51, marking the end of the project. | TRUE | 15 | 42 | 9 | 12 | 0
2 | 5 | 6 | Why is the subset of activities 4, 10, 20 not completed at time period 28? | The subset of activities 4, 10, and 20 is not completed by time period 28 because activity 20 must be completed before activity 22 can start, and activity 22 is a necessary predecessor for activity 27. This sequence continues with dependencies leading up to activity 32. Any delay in completing activity 20 would delay all subsequent dependent activities, thereby extending the overall project duration. Finishing these activities by time 28 would not allow enough time for the required sequencing and resource constraints to be satisfied, ultimately pushing the project completion time beyond the minimum possible. | FALSE | 5 | 5 | 3 | 4 | 0
2 | 5 | 6 | Why is the subset of activities 4, 10, 20 not completed at time period 28? | The subset of activities 4, 10, and 20 is not completed by time period 28 because activity 20 plays a critical role in a chain of dependent tasks that ultimately affect the overall project completion time. Specifically, activity 20 must finish before activity 22 can begin, which in turn is a prerequisite for activity 27. Activity 27 must be completed before activity 30 starts, and activity 30 must finish before the final activity, 32, can occur. Delays in any of these dependent activities would extend the project duration beyond time period 51. Therefore, the scheduling of activity 20—and by extension, activities 4 and 10—must align with the timing constraints imposed by this sequence of dependencies, preventing their early completion by time 28. | TRUE | 5 | 5 | 5 | 5 | 0
2 | 5 | 7 | Why is the subset of activities 30, 31, 32 completed at the same time period? | The subset of activities 30, 31, and 32 is completed at the same time period because they are sequentially dependent on one another and on the completion of several earlier activities. Activity 30 cannot begin until activity 27 is finished, which itself depends on activities that must be completed earlier. Similarly, activity 31 depends on the completion of both activities 24 and 28, which are constrained by their own predecessors. Activity 32, which marks the end of the project, cannot start until both activities 30 and 31 are finished. As a result of these precedence constraints and the timing of their predecessors' completion, all three activities align to finish at the same final time period, which defines the project’s minimum completion time. | FALSE | 15 | 42 | 5 | 5 | 1
2 | 5 | 7 | Why is the subset of activities 30, 31, 32 completed at the same time period? | The subset of activities 30, 31, and 32 is completed at the same time because of a chain of precedence and resource constraints that tightly link their start and finish times. Activity 30 cannot begin until activity 27 is finished, which itself depends on earlier tasks and is delayed due to competition for limited resource availability, particularly at time periods when other resource-intensive activities like 21 and 24 are active. Similarly, activity 31 cannot start until both activities 24 and 28 are completed. Activity 28, in turn, is dependent on the completion of activity 26, which is delayed because it must wait for activity 21. These dependencies create a bottleneck effect where activities 30 and 31 are delayed to the latest possible start times within the schedule. Since both 30 and 31 must finish before activity 32 can occur, and they complete at the same time, activity 32 is also scheduled at that same final time period. Delaying any one of these activities would extend the project duration beyond the current end time, so their alignment represents the most efficient schedule within the given constraints. | TRUE | 15 | 42 | 10 | 11 | 0
2 | 6 | 2 | Why is activity 31 not completed at time period 108? | Activity 31 is not completed at time period 108 because it must finish before activity 32 can begin. Since activity 32 is scheduled to start and complete at time period 47, delaying activity 31 beyond that point would prevent the project from finishing on time and would extend the overall project duration past time period 47. Therefore, activity 31 is scheduled to complete by time period 47 to ensure that all precedence constraints are met and the project completion time is minimized. | FALSE | 2 | 2 | 2 | 2 | 0
2 | 6 | 2 | Why is activity 31 not completed at time period 108? | Activity 31 is not completed at time period 108 because it must be finished before activity 32 can begin. Since activity 32 marks the end of the project and is scheduled to complete at time 47, delaying activity 31 until time 108 would extend the overall project duration beyond its current completion time. To avoid prolonging the project unnecessarily, activity 31 is scheduled earlier, ensuring that all precedence and timing constraints are respected. | TRUE | 2 | 2 | 2 | 2 | 0
2 | 6 | 4 | Why is activity 25 not completed after time period 42? | Activity 25 is not completed after time period 42 because it must finish in time to allow the subsequent activities—27, 31, and ultimately 32—to start and finish without delaying the overall project. Since activity 25 is a predecessor of activity 27, any delay in its completion would delay activity 27, which in turn would delay activity 31 and the final activity 32. This would extend the project duration beyond the planned completion time of 47, which the schedule aims to avoid. Therefore, activity 25 is scheduled to complete by time period 42 to ensure the timely progression of dependent activities and minimize the total project completion time. | FALSE | 4 | 4 | 4 | 4 | 0
2 | 6 | 4 | Why is activity 25 not completed after time period 42? | Activity 25 is not completed after time period 42 because it must finish in time for activity 27 to begin, as activity 27 depends on its completion. In turn, activity 27 must be completed before activity 31 can start, and activity 31 must finish before the final activity, 32, can occur. Delaying activity 25 beyond time period 42 would delay this entire chain of dependent activities, ultimately extending the overall project duration beyond the planned completion time of 47. To avoid prolonging the project, activity 25 must therefore be completed by time period 42. | TRUE | 4 | 4 | 4 | 4 | 0
2 | 6 | 6 | Why is the subset of activities 20, 10 not completed at time period 29? | The subset of activities 20 and 10 is not completed at time period 29 because activity 20 cannot start until activity 10 is fully completed, due to the precedence constraint. Activity 10 finishes at time 27, which means activity 20 can only begin afterward. Given that activity 20 has a duration of 2 time units, it completes at time 29. Therefore, the entire subset is only completed at the end of time period 29, not before. | FALSE | 2 | 2 | 2 | 2 | 0
2 | 6 | 6 | Why is the subset of activities 20, 10 not completed at time period 29? | The subset of activities 20 and 10 is not completed by time period 29 because activity 20 depends on the completion of activity 10 before it can begin. Since activity 10 starts at time 22 and takes 6 time units to complete, it finishes at time 27. Only after this point can activity 20 start, which it does at time 28 and completes at time 29. Therefore, the order and timing of these activities, constrained by their dependency, result in the subset not being completed until time 29. | TRUE | 2 | 2 | 2 | 2 | 0
2 | 6 | 8 | Why is the subset of activities 20, 10 not completed at the same time period? | Activities 10 and 20 are not completed at the same time because activity 20 depends on the completion of activity 10. According to the schedule, activity 10 must finish before activity 20 can begin, which is why their execution times do not overlap. This precedence constraint ensures that the project progresses in the correct order without violating any dependency or resource restrictions. | FALSE | 2 | 2 | 2 | 2 | 0
2 | 6 | 8 | Why is the subset of activities 20, 10 not completed at the same time period? | Activity 10 must be completed before activity 20 can begin, which creates a precedence constraint between them. This dependency ensures that activity 20 cannot start until activity 10 has finished. As a result, the two activities cannot be completed in the same time period. | TRUE | 2 | 2 | 2 | 2 | 0
2 | 7 | 2 | Why is activity 30 not completed at time period 90? | Activity 30 is not completed at time period 90 because it must finish before activity 32 can begin. Delaying it beyond time period 47 would extend the overall project duration, which goes against the goal of minimising the project completion time. | FALSE | 2 | 2 | 2 | 2 | 0
2 | 7 | 2 | Why is activity 30 not completed at time period 90? | Activity 30 is not completed at time period 90 because it must be completed before activity 32 can begin. Since activity 32 marks the end of the project and is scheduled to finish at time period 47, delaying activity 30 beyond this point would extend the overall project duration, violating the objective of minimizing the completion time. | TRUE | 2 | 2 | 2 | 2 | 0
2 | 7 | 4 | Why is activity 25 not completed after time period 37? | Activity 25 is not completed after time period 37 because it must be finished before activity 30 can begin, and activity 30, in turn, is a necessary predecessor for activity 32. Delaying activity 25 beyond time period 37 would postpone the start of activity 30 and ultimately extend the overall project duration beyond the planned completion time of 47. | FALSE | 3 | 3 | 3 | 3 | 0
2 | 7 | 4 | Why is activity 25 not completed after time period 37? | Activity 25 is not completed after time period 37 because it must be finished before activity 30 can begin. Since activity 30 is a prerequisite for activity 32, any delay in completing activity 25 would push the start of activity 30 later, which in turn would delay activity 32. This chain of dependencies would extend the overall project duration beyond the planned completion time of 47, violating the goal of minimising the project’s completion time. | TRUE | 3 | 3 | 3 | 3 | 0
2 | 7 | 10 | Why is activity 15 completed at time period 29 instead of activity 24? | Activity 15 is completed at time period 29 instead of an earlier time like 24 because it plays a critical role in a chain of dependent activities that ultimately determine the overall project duration. It must be completed before activity 19 can begin, which in turn affects the start of activity 23, and so on through to activity 32. Delaying activity 15 would delay the entire sequence of dependent tasks, extending the project beyond its minimum possible completion time of 47. Therefore, the schedule ensures activity 15 finishes at time 29 to keep the project on track. | FALSE | 7 | 7 | 5 | 5 | 0
2 | 7 | 10 | Why is activity 15 completed at time period 29 instead of activity 24? | Activity 15 is completed at time period 29 instead of 24 because it plays a critical role in the chain of dependencies that ultimately determine the project's overall completion time. It must be completed before activity 19 can begin, which in turn is a prerequisite for activity 23. This sequential dependency continues through activities 26 and 31, culminating in activity 32. Any delay in activity 15 directly affects all subsequent dependent activities and ultimately extends the project's duration. Therefore, to ensure the timely completion of the entire project by time period 47, activity 15 must be carefully scheduled and completed at time 29, despite not being the final activity. | TRUE | 7 | 7 | 7 | 7 | 0
2 | 8 | 1 | Why is activity 25 completed at time period 46? | Activity 25 is completed at time period 46 because it cannot start until all its predecessor activities—4, 18, and 24—are completed. In particular, activity 18 depends on activity 12, which must finish before 18 can begin. Since activity 18 finishes at time period 41, and activity 25 also requires coordination of resource availability, it starts at time period 42 and completes in 5 time units. The timing ensures both the precedence constraints and resource limitations are respected. | FALSE | 13 | 22 | 2 | 2 | 2
2 | 8 | 1 | Why is activity 25 completed at time period 46? | Activity 25 is completed at time period 46 because it depends on the completion of activity 18, which in turn cannot begin until activity 12 finishes. Activity 12 experiences delay due to high demand for a limited resource, causing a ripple effect that postpones activity 18. Since activity 25 must wait for activity 18, along with others, it cannot start earlier. This delay affects the start of activity 28, which also relies on activity 25’s completion, and continues to influence the timing of later dependent tasks. Resource constraints and task dependencies together push the entire chain of activities forward, resulting in activity 25 finishing at time 46. | TRUE | 13 | 22 | 4 | 4 | 0
2 | 8 | 2 | Why is activity 27 not completed at time period 158? | Activity 27 is not completed at time period 158 because it must be finished in time to allow the timely start of activity 31, which in turn needs to be completed before activity 32 can begin. Delaying activity 27 would push the start of activity 31 and consequently delay activity 32, extending the overall project duration beyond the intended completion time of 54. | FALSE | 3 | 3 | 3 | 3 | 0
2 | 8 | 2 | Why is activity 27 not completed at time period 158? | Activity 27 is not completed at time period 158 because it must finish before activity 31 can begin, and activity 31 in turn must be completed before activity 32 starts. Since activity 32 marks the end of the project and occurs at time period 54, delaying activity 27 until time period 158 would postpone activity 31 and subsequently activity 32, extending the project far beyond its actual completion time. This would violate the precedence constraints and the goal of minimising the project duration. | TRUE | 3 | 3 | 3 | 3 | 0
2 | 8 | 3 | Why is activity 32 not completed before time period 54? | Activity 32 is not completed before time period 54 because it depends on the completion of several preceding activities. These include a sequence of dependent tasks starting with activity 12, which must be completed before activity 18 can begin. Activity 18 then enables activity 25, which in turn is a prerequisite for activity 28. Activity 28 must finish before activity 30 can start, and activity 30 is one of the final prerequisites for activity 32. Additionally, activity 23 must be completed before activity 27, which is required for activity 31—another direct predecessor of activity 32. These interdependencies, combined with resource limitations at certain time periods, delay the completion of these activities, ultimately preventing activity 32 from being completed any earlier than time period 54. | FALSE | 14 | 29 | 8 | 6 | 0
2 | 8 | 3 | Why is activity 32 not completed before time period 54? | Activity 32 is not completed before time period 54 because it depends on the completion of activities 30 and 31. Activity 30 cannot start until activity 28 is finished, which in turn is delayed by the completion of activity 25. Activity 25 is dependent on activity 18, which can only begin after activity 12 is completed. Similarly, activity 31 relies on activity 27, which is delayed due to the sequence of activities leading up to it, including activity 23. Additionally, resource constraints—especially the limited availability of resource 1—affect the scheduling of activities like 27, 28, and 31, causing further delays. These interconnected dependencies and resource limitations ultimately push the completion of all prerequisite activities to time period 54, preventing activity 32 from being completed any earlier. | TRUE | 14 | 29 | 10 | 14 | 0
2 | 8 | 4 | Why is activity 25 not completed after time period 46? | Activity 25 is not completed after time period 46 because it must finish in time to allow the timely start of activity 28, which depends on it. Delaying activity 25 would delay activity 28, which in turn would postpone the start of activity 30 and ultimately extend the overall project duration beyond its current completion time of 54. To avoid lengthening the project schedule, activity 25 is scheduled to be completed by time 46. | FALSE | 4 | 4 | 3 | 3 | 0
2 | 8 | 4 | Why is activity 25 not completed after time period 46? | Activity 25 is not completed after time period 46 because it must finish in time for activity 28 to start, as activity 28 directly depends on it. Activity 28, in turn, is a prerequisite for activity 30, which must be completed before the final activity, 32, can begin. Delaying activity 25 would delay this entire chain of dependent tasks, ultimately extending the project's completion time beyond the planned end at time period 54. To avoid this, activity 25 is scheduled to finish by time 46 to maintain the overall project timeline. | TRUE | 4 | 4 | 4 | 4 | 0
2 | 8 | 6 | Why is the subset of activities 20, 24, 9 not completed at time period 29? | The subset of activities 20, 24, and 9 is not completed at time period 29 because activity 24 cannot start until activity 9 is completed. Since activity 9 finishes at time 28, activity 24 can only begin afterward and completes at time 29. Therefore, although activity 20 also finishes at time 29, the entire subset is only completed at the end of that period, not before. | FALSE | 2 | 3 | 1 | 1 | 0
2 | 8 | 6 | Why is the subset of activities 20, 24, 9 not completed at time period 29? | The subset of activities 20, 24, and 9 is not completed at time period 29 because activity 24, which must be completed by that time, depends on the prior completion of activity 9. Since activity 9 only finishes at time 28, activity 24 cannot start until after that. As a result, activity 24 starts at time 29, meaning it is still in progress during that period and not yet completed. | TRUE | 2 | 3 | 2 | 2 | 1
2 | 8 | 8 | Why is the subset of activities 20, 24, 9 not completed at the same time period? | The subset of activities 20, 24, and 9 is not completed at the same time because there are precedence constraints that must be respected. Specifically, activity 24 cannot start until activity 9 is completed, as it is one of its predecessors. This dependency enforces a sequential order, preventing these activities from being completed simultaneously. | FALSE | 2 | 3 | 1 | 1 | 0
2 | 8 | 8 | Why is the subset of activities 20, 24, 9 not completed at the same time period? | The subset of activities 20, 24, and 9 is not completed at the same time because there are precedence constraints that require certain activities to be completed before others can begin. Specifically, activity 9 must finish before activity 24 can start, and activity 24 must be completed as part of the project. This dependency creates a sequence where activity 9 finishes first, followed by activity 24, preventing all three activities from being completed simultaneously. | TRUE | 2 | 3 | 2 | 3 | 0
2 | 8 | 9 | Why is activity 25 completed at time period 46 instead of time period 45? | Activity 25 is completed at time period 46 instead of 45 because it cannot start until all its predecessor activities—activities 4, 18, and 24—are finished. Among these, activity 18 finishes at time period 41, allowing activity 25 to start no earlier than time period 42. Given its duration of 5 time units, it completes at time period 46. This scheduling ensures that all precedence constraints are respected while also considering the availability of required resources during the scheduled period. | FALSE | 14 | 22 | 1 | 1 | 0
2 | 8 | 9 | Why is activity 25 completed at time period 46 instead of time period 45? | Activity 25 is completed at time period 46 instead of 45 because its start is delayed by the need to wait for the completion of activity 18, which itself depends on the completion of activity 12. Activity 12 cannot start earlier due to resource constraints involving resource type 4, which is heavily used by other concurrent activities. These dependencies create a chain reaction that pushes the start time of activity 25 later. Additionally, activity 25 cannot begin until all its predecessors, including activities 4, 18, and 24, are completed. The culmination of these precedence and resource constraints results in activity 25 finishing at time 46. | TRUE | 14 | 22 | 3 | 3 | 0
2 | 9 | 2 | Why is activity 21 not completed at time period 83? | Activity 21 is not completed at time period 83 because it plays a critical role in the sequence of dependent activities that determine the project’s overall duration. It must be completed early enough to allow activity 26 to start, which in turn enables activity 30 to begin, leading to the timely completion of activity 32. Delaying activity 21 would delay this entire chain and extend the project’s completion time beyond 54, which contradicts the goal of minimising the project duration. | FALSE | 4 | 4 | 4 | 4 | 0
2 | 9 | 2 | Why is activity 21 not completed at time period 83? | Activity 21 is not completed at time period 83 because it plays a crucial role in a chain of dependent activities that ultimately determine the project’s completion time. It must finish before activity 26 can begin, which in turn must be completed before activity 30 starts. Since activity 30 is a direct predecessor to the final activity, 32, any delay in completing activity 21 would delay the entire sequence, pushing the project completion beyond the current end time of 54. To avoid extending the overall project duration, activity 21 must be completed earlier in the schedule. | TRUE | 4 | 4 | 4 | 4 | 0
2 | 9 | 5 | Why is the subset of activities 30, 32 completed at time period 54? | The subset of activities 30 and 32 is completed at time period 54 because activity 30 depends on the completion of several preceding activities, including 24 and 26, which themselves rely on a sequence of earlier tasks. Delays in these prior activities, due to both precedence constraints and limited resource availability, push the start of activity 30 to a later time. Activity 32, which marks the end of the project, can only begin once activity 30 and other dependencies are completed. Therefore, the entire chain of dependencies and resource constraints culminates in the project finishing at time period 54. | FALSE | 13 | 24 | 3 | 3 | 0
2 | 9 | 5 | Why is the subset of activities 30, 32 completed at time period 54? | The subset of activities 30 and 32 is completed at time period 54 due to a chain of precedence and resource constraints that delay their execution. Activity 30 depends on the completion of activities 24 and 26, which themselves are delayed by their own predecessors. Activity 24 cannot start until activity 20 is finished, and activity 20 is delayed because it must wait for activity 11, which is affected by resource limitations. Similarly, activity 26 depends on activity 16, which requires activity 12 to finish first. Activity 12, in turn, depends on activity 9. These dependencies form a connected path of constraints that push the start of activity 30 later in the schedule. Since activity 32 can only begin after activity 30 is completed, the entire subset finishes at time period 54, which becomes the project’s completion time. | TRUE | 13 | 24 | 9 | 9 | 0
2 | 9 | 7 | Why is the subset of activities 30, 32 completed at the same time period? | The subset of activities 30 and 32 is completed at the same time period because activity 32 depends on the completion of activity 30, which in turn cannot start until both activities 24 and 26 are finished. These dependencies are the result of a chain of precedence constraints beginning with earlier activities like 9, 11, 12, 16, and 20. Additionally, resource limitations at certain time periods delay the start of some activities, contributing to the overall scheduling of dependent tasks. As a result, all these constraints align the completion of activity 30 with the end of the project at activity 32, which has zero duration. | FALSE | 13 | 24 | 5 | 3 | 1
2 | 9 | 7 | Why is the subset of activities 30, 32 completed at the same time period? | The subset of activities 30 and 32 is completed at the same time because activity 32 depends on the completion of activity 30, which in turn cannot begin until both activities 24 and 26 are finished. Activity 24 relies on the completion of activity 20, which is delayed by its dependency on activity 11. Similarly, activity 26 depends on activity 16, which follows activity 12, and that in turn cannot start before activity 9 is completed. These interconnected precedence constraints, along with limited resource availability at critical time periods, delay the start times of these activities. As a result of these cascading dependencies and resource constraints, activity 30 finishes at time 54, and since activity 32 has no duration and depends on activity 30, it is also completed at the same time, marking the end of the project. Any delay in this chain would extend the project beyond time 54, so the schedule aligns their completion to minimize the overall project duration. | TRUE | 13 | 24 | 11 | 9 | 0
2 | 9 | 10 | Why is activity 11 completed at time period 32 instead of activity 28? | Activity 11 is completed at time period 32 instead of activity 28 because its timely completion is critical to the progression of several dependent activities that directly influence the overall project duration. Specifically, activity 11 must finish before activity 20 can begin, which in turn is a prerequisite for activity 24. Activity 24 is then required to start activity 30, which is one of the final steps before project completion at activity 32. Delaying activity 11 would postpone all these subsequent tasks and extend the total project duration. Additionally, resource constraints at earlier time periods, particularly the limited availability of resource type 3, prevent both activities 11 and 28 from progressing simultaneously. As a result, priority is given to activity 11 to maintain the shortest possible project completion time. | FALSE | 13 | 23 | 7 | 9 | 0
2 | 9 | 10 | Why is activity 11 completed at time period 32 instead of activity 28? | Activity 11 is completed at time period 32 instead of activity 28 because it plays a critical role in the sequence of dependent tasks that directly affect the project's overall completion time. Specifically, activity 11 must be completed before activity 20 can begin, and activity 20, in turn, is a prerequisite for activity 24, which leads to activity 30 and ultimately to the final activity 32. Any delay in activity 11 delays this entire chain, extending the project timeline. Additionally, resource constraints—particularly the limited availability of resource type 3—affect when activity 11 can be scheduled. Resource 3 is heavily used around the same time by multiple activities, including 9, 15, and 28, which creates competition and limits scheduling flexibility. Moreover, activities like 9 and 12 must also be completed in a timely manner to maintain the critical path. Therefore, prioritising the completion of activity 11 ensures the continuation of key dependent activities and prevents the extension of the project's duration beyond the final completion time of 54. | TRUE | 13 | 23 | 9 | 11 | 0
2 | 10 | 1 | Why is activity 25 completed at time period 22? |  | FALSE | 28 | 108
2 | 10 | 1 | Why is activity 25 completed at time period 22? |  | TRUE | 28 | 108
2 | 10 | 2 | Why is activity 30 not completed at time period 105? | Activity 30 is not completed at time period 105 because it must be finished by time 43 in order for activity 32, which depends on it, to start and complete at that same time. Delaying activity 30 beyond time 43 would extend the overall project duration, violating the goal of minimizing the project completion time. | FALSE | 2 | 2 | 2 | 2 | 0
2 | 10 | 2 | Why is activity 30 not completed at time period 105? | Activity 30 is not completed at time period 105 because it must finish before activity 32 can begin, and activity 32 marks the end of the project. Delaying activity 30 to time 105 would extend the overall project duration well beyond its current completion time of 43, violating the goal of minimising the project completion time. | TRUE | 2 | 2 | 2 | 2 | 0
2 | 10 | 4 | Why is activity 25 not completed after time period 22? | Activity 25 is not completed after time period 22 because delaying its completion would postpone the start of activity 26, which in turn would delay a sequence of dependent activities including 27, 28, and 30. This chain of dependencies ultimately leads to the final activity, and any delay in activity 25 would extend the overall project duration beyond the planned completion time of 43. To minimize the total project duration, activity 25 must be completed at time period 22. | FALSE | 6 | 6 | 6 | 6 | 0
2 | 10 | 4 | Why is activity 25 not completed after time period 22? | Activity 25 is not completed after time period 22 because it serves as a critical predecessor in a chain of dependent activities that ultimately determine the project’s completion time. It must finish before activity 26 can begin, which in turn must be completed before activity 27 starts. This sequence continues through activities 28 and 30, all the way to the final activity, 32. Any delay in completing activity 25 would delay the entire chain, extending the overall project duration beyond the planned completion time of 43. Therefore, completing activity 25 by time 22 is necessary to avoid a delay in the project schedule. | TRUE | 6 | 6 | 6 | 6 | 0
2 | 10 | 6 | Why is the subset of activities 14, 19, 25, 15, 21 not completed at time period 22? | The subset of activities 14, 19, 25, 15, and 21 is not completed at time period 22 because the completion of these activities is constrained by both precedence and resource limitations. Some of these activities depend on the completion of earlier tasks, which delays their start times. Additionally, limited availability of resources, particularly resource type 2, causes contention among concurrent activities, further delaying their execution. These delays propagate through the project schedule, contributing to a later overall project completion time. | FALSE | 7 | 8 | 2 | 0 | 0
2 | 10 | 6 | Why is the subset of activities 14, 19, 25, 15, 21 not completed at time period 22? | The subset of activities 14, 19, 25, 15, and 21 is not completed by time period 22 due to constraints related to limited resource availability and precedence relationships among activities. Specifically, resource type 2 is heavily used at that time by several other activities, including activity 24, which must be completed before activity 27 can begin. This, in turn, delays activity 28 and subsequently activity 30, which must finish before the project can be completed. These dependencies form a chain that extends the overall project duration and prevents the subset of activities from finishing by time period 22. | TRUE | 7 | 8 | 6 | 5 | 0
2 | 10 | 8 | Why is the subset of activities 14, 19, 25, 15, 21 not completed at the same time period? |  | FALSE | 28 | 133
2 | 10 | 8 | Why is the subset of activities 14, 19, 25, 15, 21 not completed at the same time period? |  | TRUE | 28 | 133
2 | 10 | 9 | Why is activity 25 completed at time period 22 instead of time period 21? |  | FALSE | 20 | 40
2 | 10 | 9 | Why is activity 25 completed at time period 22 instead of time period 21? |  | TRUE | 20 | 40
2 | 10 | 10 | Why is activity 19 completed at time period 22 instead of activity 15? |  | FALSE | 18 | 68
2 | 10 | 10 | Why is activity 19 completed at time period 22 instead of activity 15? |  | TRUE | 18 | 68